## Tabelle1
Calendar Week
Task | Target FB (h) | Target LJ (h) | Actual FB (h) | Actual LJ (h) | 38 | 39 | 40 | 41 | 42 | 43 |  | 44 | 45 |  | 46 | 47 | 48 | 49 |  | 50 | 51
Project start
Problem analysis and concept discussion | 8 | 8 | 6 | 6
Administration and project planning | 5 | 5 | 5 | 5
Rapid prototyping for concept validation | 10
Hardware
Detail block diagram and core component evaluation |  | 5
Schematic design, bill of material (BOM) and Component ordering | 12 | 15
Mechanical design (e.g. Case evaluation) | 5
PCB Layout | 12 | 12
Review and production preparation | 5 | 5
Assembly and testing | 5 | 5
Firmware | [8 empty] | MS1
Familiarization with IDE, programmer, RTOS, chip periphery | 10
Concept design | 5 | 5
Implementation of file system | 15
Implementation of USB-Interface | 20
Implementation of CAN-Interface |  | 5
Implementation of LAN/WLAN-Interface |  | 30
Implementation of IMU |  | 5
Configuration file loading and parsing | 15
FMS-Package parser and data packing |  | 30
Integration of modules and main application | 25 | 20
Backend Software | [16 empty] | MS2
Implementation of network interface |  | 10
Data fetching, processing and storing |  | 15
Implementation of file serving for device | 5
Graphical Visualizer | 10
Configuration file creator | 8
System testing
Use Case 1 | 8 | 8
Use Case 2 | 5 | 5
Use Case 3 | 5 | 5
Documentation | [18 empty] | MS3
Requirements Specification / Report | 40 | 40 | 5 | 5
Abstract / Poster / Elevator speech (video) | 7 | 7
Total (h): | 240 | 240 | 16 | 16 | [13 empty] | MS4 |  |  | MS5
[5 empty] | Florian Baumgartner Target | [5 empty] | Milestone |  |  | Description
[5 empty] | Florian Baumgartner Actual | [5 empty] | MS1 |  |  | Hardware design finished and production start
[5 empty] | Luca Jost Target | [5 empty] | MS2 |  |  | Firmware key-requirements implemented
[5 empty] | Luca Jost Actual | [5 empty] | MS3 |  |  | System integration tests validated
[5 empty] | Both Target | [5 empty] | MS4 |  |  | Submission date for abstract: 10.12.2021
[5 empty] | Both Actual | [5 empty] | MS5 |  |  | Submission date for thesis and video: 23.12.2021