## Tabelle1
Calendar Week
Task | Target FB (h) | Target LJ (h) | Actual FB (h) | Actual LJ (h) | 38 | 39 | 40 | 41 | 42 | 43 |  | 44 | 45 |  | 46 | 47 | 48 | 49 | 50 | 51
Project start
Problem analysis and concept discussion
Administration and project planning
Rapid prototyping for concept validation
Hardware
Detail block diagram and core component evaluation
Schematic design, bill of material (BOM) and Component ordering
Mechanical design (e.g. Case evaluation)
PCB Layout
Review and production preparation
Assembly and testing
Firmware
Familiarization with IDE, programmer, RTOS, chip periphery
Concept design
Implementation of SD-Card and file system
Implementation of USB-Interface
Implementation of CAN-Interface
Implementation of WLAN-Interface
Implementation of Ethernet-Interface
FMS-Package parser and data packing
Over-The-Air-Update and config file
Integration of modules and main application
Backend Software
Implementation of network interface
Data fetching, processing and storing
Implementation of Firmware and config download
UC1, Driving Quality Analysis
UC2, Vehicle Maintenance Report
System testing
UC1
UC2
Documentation
Report
Abstract / Poster / Elevator speed (video) / Finishing touches
Total (h):
[5 empty] | Florian Baumgartner Target | [5 empty] | Milestone |  |  | Description
[5 empty] | Florian Baumgartner Actual | [5 empty] | MS1 |  |  | Hardware design finished and production start
[5 empty] | Luca Jost Target | [5 empty] | MS2 |  |  | Firmware key-requirements implemented
[5 empty] | Luca Jost Actual | [5 empty] | MS3 |  |  | System integration tests validated
[5 empty] | Both Target | [5 empty] | MS4 |  |  | Submission date for abstract: 10.12.2021
[5 empty] | Both Actual | [5 empty] | MS5 |  |  | Submission date for thesis and video: 23.12.2021